## GanttChart
Using AI for Intelligent stock trading
Capstone Code: SP25AI37
| Capstone Start Date: |  | 2025-01-08 |  | Tuần hiển thị: |  | 1 | Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4 | [6 empty] | Week 5 | [6 empty] | Week 6 | [6 empty] | Week 7 | [6 empty] | Week 8 | [6 empty] | Week 9 | [6 empty] | Week 10 | [6 empty] | Week 11 | [6 empty] | Week 12 | [6 empty] | Week 13 | [6 empty] | Week 14 | [6 empty] | Week 15
| Capstone Management: |  | Nguyễn Việt Anh |  |  |  |  | 2025-01-06 | [6 empty] | 2025-01-13 | [6 empty] | 2025-01-20 | [6 empty] | 2025-01-27 | [6 empty] | 2025-02-03 | [6 empty] | 2025-02-10 | [6 empty] | 2025-02-17 | [6 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14
Capstone Resources | time axis 2025-01-06 to 2025-04-20
ID | Tasks | Workers | Start | End | Days | % complete | Workday | [105 empty] | Input resources | Output resources | Task page | time axis 2025-01-06 to 2025-04-20
1 | Make Idea and division of work tasks |  | 2025-01-09 | 2025-01-22 | 42 |  | 30
1.1 | Idea + work tasks | Hoàng xuân cảnh | 2025-01-09 | 2025-01-22 | 14 | 100% | 10 | [105 empty] | Using AI for Intelligent stock trading | Propose solution
1.2 | Idea + work tasks | Hoàng văn Bắc | 2025-01-09 | 2025-01-22 | 14 | 100% | 10 | [105 empty] | Using AI for Intelligent stock trading | Propose solution
1.3 | Idea + work tasks | Nguyễn Việt Anh | 2025-01-09 | 2025-01-22 | 14 | 100% | 10 | [105 empty] | Using AI for Intelligent stock trading | Propose solution
1.4
2 | Data collection |  | 2025-01-23 | 2025-02-05 | 42 |  | 30 | bar: 2025-01-06 to 2025-01-22; 2025-02-06 to 2025-04-20
2.1 | From SSI | Hoàng xuân cảnh | 2025-01-23 | 2025-02-05 | 14 | 100% | 10 | [105 empty] | data collection requirements | Data collection
2.2 | From Vnstock | Hoàng văn Bắc | 2025-01-23 | 2025-02-05 | 14 | 100% | 10 | [105 empty] | data collection requirements | Data collection
2.3 | From Global Factor Data | Nguyễn Việt Anh | 2025-01-23 | 2025-02-05 | 14 | 100% | 10 | [105 empty] | data collection requirements | Data collection
2.4
3 | Research methods |  | 2025-02-06 | 2025-03-26 | 49 |  | 35
3.1 | Feature Engineering and Label Generation for BB | Nguyễn Việt Anh | 2025-02-06 | 2025-03-03 | 26 | 100% | 18 | [105 empty] | Propose solution BB | Code BB
3.2 | Evaluation of Feature Engineering Results for BB | Nguyễn Việt Anh | 2025-03-04 | 2025-03-08 | 5 | 100% | 4 | [106 empty] | Feature engineering BB
3.3 | Feature Engineering and Label Generation for UD | Nguyễn Việt Anh | 2025-03-09 | 2025-03-17 | 9 | 100% | 6 | [105 empty] | Propose solution UD | Code UD
3.4 | Evaluation of Feature Engineering Results for UD | Nguyễn Việt Anh | 2025-03-18 | 2025-03-22 | 5 | 100% | 4 | [106 empty] | Feature engineering UD
3.5 | Global Factor Data | Nguyễn Việt Anh | 2025-03-23 | 2025-03-24 | 2 | 100% | 1 | [105 empty] | Propose solution MF | on Excel MF
3.6 | Evaluation of Results under Feature Transformation | Nguyễn Việt Anh | 2025-03-25 | 2025-03-26 | 2 | 100% | 2 | [106 empty] | Feature engineering MF
3.7
4 | Multi-Factor Model |  | 2025-03-27 | 2025-04-08 | 13 |  | 9
4.1 | Portfolio Return Explanation and Prediction | Nguyễn Việt Anh | 2025-03-27 | 2025-04-08 | 13 | 100% | 9 | [105 empty] | Feature engineering MF | Code MF
4.2
5 | Module 1 design |  | 2025-02-06 | 2025-04-09 | 63 |  | 45
5.1 | Building a program for BB | Hoàng văn Bắc | 2025-02-06 | 2025-03-09 | 32 | 100% | 22 | [105 empty] | Feature engineering BB | Code BB
5.2 | Evaluation of BB model construction results | Hoàng văn Bắc | 2025-03-10 | 2025-03-18 | 9 | 100% | 7 | [106 empty] | Metrix BB
5.3 | Building a program for UD | Hoàng văn Bắc | 2025-03-19 | 2025-04-02 | 15 | 100% | 11 | [105 empty] | Feature engineering UD | Code UD
5.4 | Evaluation of UD model construction results | Hoàng văn Bắc | 2025-04-03 | 2025-04-09 | 7 | 100% | 5 | [106 empty] | Metrix UD
5.5 | [113 empty] | API BB_UD
6 | System design and implementation |  | 2025-02-06 | 2025-04-10 | 64 |  | 46 | [105 empty] | Data collection
6.1 | Front -end | Hoàng xuân cảnh | 2025-02-06 | 2025-03-19 | 42 | 100% | 30 | [105 empty] | API BB_UD
6.2 | Back-end | Hoàng xuân cảnh | 2025-03-20 | 2025-04-10 | 22 | 100% | 16 | [105 empty] | Code MF | Web
6.3
7 | Project Report |  | 2025-04-09 | 2025-04-22 | 25 |  | 20 | [106 empty] | Capstone Project Document | 0-93
7.1 | 0. Slide | Nguyễn Việt Anh | 2025-04-09 | 2025-04-09 | 1 | 100% | 1
7.2 | I. ​​Project Introduction | Nguyễn Việt Anh | 2025-04-10 | 2025-04-10 | 1 | 100% | 1 | [107 empty] | 15-20
7.3 | II. Project Management Plan | Hoàng văn Bắc | 2025-04-10 | 2025-04-10 | 1 | 100% | 1 | [107 empty] | 21-26
7.4 | III. Existing Systems/State of the Art | Nguyễn Việt Anh | 2025-04-11 | 2025-04-13 | 3 | 100% | 1 | [107 empty] | 27-29
7.5 | IV.A. Research Questions and Objectives Based on Collected Data | Nguyễn Việt Anh | 2025-04-14 | 2025-04-16 | 3 | 100% | 3 | [107 empty] | 30-42
7.6 | IV.B. Module 1 design | Hoàng văn Bắc | 2025-04-11 | 2025-04-16 | 6 | 100% | 4 | [107 empty] | 44-76
7.7 | 1.2.2. SVM Model | Nguyễn Việt Anh | 2025-04-17 | 2025-04-17 | 1 | 100% | 1 | [107 empty] | 50-51
7.8 | IV.C. Multi-Factor Model for Portfolio Return Explanation and Prediction | Nguyễn Việt Anh | 2025-04-18 | 2025-04-18 | 1 | 100% | 1 | [107 empty] | 77-79
7.9 | V. System Design and Implementation (Web) | Hoàng xuân cảnh | 2025-04-11 | 2025-04-16 | 6 | 100% | 4 | [107 empty] | 81-85
7.10 | VI. Results and Discussion | Nguyễn Việt Anh | 2025-04-19 | 2025-04-21 | 3 | 100% | 1 | [107 empty] | 87-90
7.11 | VII. Conclusion | Nguyễn Việt Anh | 2025-04-22 | 2025-04-22 | 1 | 100% | 1 | [107 empty] | 91-93
[114 empty] | Member | Workday
[114 empty] | Nguyễn Việt Anh | 74
[114 empty] | Hoàng xuân cảnh | 70
[114 empty] | Hoàng văn Bắc | 70
Bubble | bar: 2025-04-20
Up or Down | bar: 2025-04-20
Multi-Factor Model | bar: 2025-04-20
Formulas:
Week 1 = [Week 1, row below]
Week 2 = [Week 2, row below]
Week 3 = [Week 3, row below]
Week 4 = [Week 4, row below]
Week 5 = [Week 5, row below]
Week 6 = [Week 6, row below]
Week 7 = [Week 7, row below]
Week 8 = [Week 8, row below]
Week 9 = [Week 9, row below]
Week 10 = [Week 10, row below]
Week 11 = [Week 11, row below]
Week 12 = [Week 12, row below]
Week 13 = [Week 13, row below]
Week 14 = [Week 14, row below]
Week 15 = [Week 15, row below]
Start = MIN([Start, row below]:E11)
Start = MIN([Start, row below]:D28)
End = MAX([Start, row below]:E11)
End = [Start]+[Tuần hiển thị:]-1
Workday = NETWORKDAYS([Start, row below],[End, row below])+NETWORKDAYS(D10,E10)+NETWORKDAYS(D11,E11)
Workday = NETWORKDAYS([Start],[End])

## IDEAS
| Name | Propose solution | Supervisor
1. | Hoang Xuan Canh | Idea for the Web | Trần Trọng Huỳnh
2. | Hoang van Bac | Idea for the BB, UD
3. | Nguyen Viet Anh | Idea for the Multi-Factor Model

## Data collections
| Name | requirements
1. | Hoang Xuan Canh | collect data for the BB, UD 1
2. | Hoang van Bac | collect data for the BB, UD 2
3. | Nguyen Viet Anh | collect data for the Multi-Factor Model